## Sprint 1 Daily Scrum Document
Teammate | Question | Week 1 |  |  |  |  | Week 2
|  | Tuesday | Wednesday | Tuesday | Wednesday | Thursday | Sunday | Monday | Tuesday | Wednesday | Thursday
Margot Arthur | What did you do yesterday? | I have completed the UI overlook design of the product page that I have working on. | I have completed the design of some of the assets such as addition/removal icon and cart icon.
| What will you do today? | I will be designing some nessecarry assets for the product page such as the addition and cart icon. | I will be brainstorming and researching some ideas for the cart page.
| Did you have any obstacles? | I ran into some license problems while extracing the adobe XD UI. | No
Hinata Haruki | What did you do yesterday? | I was researching some free source open APIs that I can use as a simulation and various ways of Implementing. | I Have Implemented the basic Nesscary enviroment for Express JS.
| What will you do today? | I will be setting up the necessary Express JS Enviroment for setting up the APIs. | I will work on simulating an API response to speed up the backend work and functionality implementation for my team.
| Did you have any obstacles? | No | I had a network problem, that blocked some of APIs and their pages so I contacted the IT/Network team and the problem was solved.

## Sprint 2 Daily Scrum Document
Teammate | Question | Week 4 |  |  |  |  | Week 2
|  | Monday | Tuesday | Tuesday | Wednesday | Thursday | Sunday | Monday | Tuesday | Wednesday | Thursday
Sakura Yamato | What did you do yesterday? | I was working on designing a visual presentation of a three user privilege system for facilitating the implementation. | Finalizied the skeleton model of the three priviledge system.
| What will you do today? | Finalizing and comparing the presented privelege system design to popular systems and setting up the popular coding enivorment. | Working on implementing the user authentication.
| Did you have any obstacles? | No | No
Kareem Ayman | What did you do yesterday? | Researched various SQL injection methods and automated tools. | setted up the automated SQL injection tools for testing.
| What will you do today? | Setting up the automated enviroment for the testing. | Running the automated tested and filling the reports of the system behaviour.
| Did you have any obstacles? | Legality and law issues of the usage of certain tools, but finally got an approval of using them for private institutions and testing purposes. | No